## Sheet1
Library Management System
Work Breakdown Schedule for Library Management System
WBS | Task | Start Date | End Date | Duration (In Days) | Notes | Responsible Team Member
| Project: Library Management System | 2020-10-21 | 2020-12-15 | 56
1 | Form Team | 2020-10-21 | 2020-10-27 | 7 |  | All
1.1 | Form group and make introductions | 2020-10-27 | 2020-10-27 | 1 |  | All
1.2 | Create group communication page, file storage | 2020-10-27 | 2020-10-28 | 2 | GitHub, email, Google Meet | Scott
1.3 | Submit group members | 2020-10-27 | 2020-10-27 | 1 |  | Gonghweh
2 | Project Plan | 2020-10-28 | 2020-11-03 | 7 |  | Cindy
2.1 | Requirements | 2020-10-29 | 2020-11-03 | 6
2.2 | Submit to group page | 2020-11-03 | 2020-11-03 | 1
2.3 | Complete and submit Project Plan | 2020-11-04 | 2020-11-04 | 1
3 | Test Plan | 2020-11-09 | 2020-11-15 | 7 |  | Cindy
3.1 | Research and collaborate on test requirements, test data, and test plan |  | 2020-11-11
3.2 | Submit outline to group page. |  | 2020-11-11
3.3 | Work on Test Plan |  | 2020-11-15
3.4 | Complete and submit Test Plan |  | 2020-11-15
4 | User’s Guide
4.1 | Submit outline to group page |  | 2020-11-13
4.2 | Submit preliminary guide |  | 2020-11-17
4.3 | Complete and submit User’s Guide |  | 2020-12-08
5 | Design | 2020-11-02 | 2020-11-08 | 7
5.1 | Research and collaborate on application design |  | 2020-11-06
5.2 | Finalize design decisions |  | 2020-11-07
5.3 | Submit outline to group page |  | 2020-11-06
5.4 | Work on Project Design |  | 2020-11-10
5.5 | Complete and submit Project Design |  | 2020-11-08
6 | Coding/Implementation | 2020-11-16 | 2020-12-13
6.1 | Phase 1 Source |  | 2020-11-22
6.2 | Phase 2 Source |  | 2020-11-29
6.3 | Phase 3 Source |  | 2020-12-06
7 | Testing |  |  |  |  | Cindy
7.1
8 | Peer Reviews
8.1 | Peer Review 1 | 2020-11-19 | 2020-11-25 | 7
8.2 | Peer Review 2 | 2020-11-26 | 2020-12-02 | 7
8.3 | Peer Review 3 | 2020-12-03 | 2020-12-09 | 7
9 | Submit final project/deliverables |  | 2020-12-15