## WBS & Key Milestones
Group 1
Project: Library Management System
Work Breakdown Structure (WBS) | [6 empty] | Peer Reviews Schedule |  |  |  |  | Key Milestones (Status: To do, In-progress, Completed)
WBS | Task | Start Date | End Date | Duration (In Days) | Notes | Responsible Team Member | Task | Start Date | End Date | Duration (In Days) | Responsible Team Member | Milestone | WBS | Responsible Team Member | Due Date | Status
| Project: Library Management System | 2020-10-21 | 2020-12-15 | 56 |  |  | Peer Review 1 | 2020-11-19 | 2020-11-25 | 7 | Jonathan | Group member names and topic submitted | 1.3 | Gonghweh | 2020-10-27 | Completed
1 | Form Team | 2020-10-21 | 2020-10-27 | 7 |  | All | Complete and submit Peer Review 1 | 2020-11-25 | 2020-11-25 | 1 |  | Project Plan complete and submitted | 2.7 | Cynthia | 2020-11-04 | Completed
1.1 | Form group and make introductions | 2020-10-27 | 2020-10-27 | 1 |  | All | Peer Review 2 | 2020-11-26 | 2020-12-02 | 7 | Gonghweh | Finalize Design decisions | 3.2 | Gonghweh | 2020-11-08 | To do
1.2 | Create group communication page, file storage | 2020-10-27 | 2020-10-28 | 2 | GitHub, email, Google Meet | Scott | Complete and submit Peer Review 2 | 2020-12-02 | 2020-12-02 | 1 |  | Project Design complete and submitted | 3.5 | Gonghweh | 2020-11-11 | To do
1.3 | Submit group members | 2020-10-27 | 2020-10-27 | 1 |  | Gonghweh | Peer Review 3 | 2020-12-03 | 2020-12-09 | 7 | Scott | Test Plan complete and submitted | 4.4 | Jonathan | 2020-11-18 | To do
2 | Project Plan | 2020-10-29 | 2020-11-04 | 7 |  | Cynthia | Complete and submit Peer Review 3 | 2020-12-09 | 2020-12-09 | 1 |  | Coding/Implementation Phase 1 | 5.1.1 | Scott | 2020-11-25 | To do
2.1 | Define Requirements | 2020-10-29 | 2020-11-03 | 6 | [7 empty] | Coding/Implementation Phase 2 | 5.2.1 | Scott | 2020-12-02 | To do
2.2 | Submit Requirements to GitHub | 2020-11-03 | 2020-11-03 | 1 | [7 empty] | Coding/Implementation Phase 3 | 5.3.1 | Scott | 2020-12-09 | To do
2.3 | Complete and submit Project Plan to Assignment folder | 2020-11-04 | 2020-11-04 | 1 | [7 empty] | Coding/Implementation Phase Final | 5.4 | Scott | 2020-12-15 | To do
3 | Design | 2020-11-05 | 2020-11-11 | 7 |  | Gonghweh | [5 empty] | Testing* | 7.1 | Jonathan | TBD | To do
3.1 | Research and collaborate on application design | 2020-11-05 | 2020-11-07 | 3 | [7 empty] | User’s Guide complete | 6.2 | Cynthia | 2020-12-08 | To do
3.2 | Finalize design decisions | 2020-11-05 | 2020-11-08 | 4 | [7 empty] | Final project deliverables submitted | 8 | Cynthia | 2020-12-15 | To do
3.3 | Submit outline to GitHub | 2020-11-05 | 2020-11-07 | 3 | [7 empty] | * Testing milestones will be outlined once the Test Plan has been finalized.
3.4 | Work on Project Design | 2020-11-08 | 2020-11-11 | 4
3.5 | Complete and submit Project Design to Assignment folder | 2020-11-11 | 2020-11-11 | 1
4 | Test Plan | 2020-11-12 | 2020-11-18 | 7 |  | Jonathan
4.1 | Research and collaborate on test requirements, test data, and test plan | 2020-11-12 | 2020-11-14 | 3
4.2 | Submit outline to GitHub. | 2020-11-12 | 2020-11-14 | 3
4.3 | Work on Test Plan | 2020-11-15 | 2020-11-18 | 4
4.4 | Complete and submit Test Plan to Assignment folder | 2020-11-18 | 2020-11-18 | 1
5 | Coding/Implementation | 2020-11-19 | 2020-12-15 | 28 |  | Scott
5.1 | Phase 1 Source | 2020-11-19 | 2020-11-25 | 7 | Will follow the design phase
5.1.1 | Complete and submit Phase 1 Source code to Assignment folder | 2020-11-25 | 2020-11-25 | 1
5.2 | Phase 2 Source | 2020-11-26 | 2020-12-02 | 7 | Will follow the design phase
5.2.1 | Complete and submit Phase 2 Source code to Assignment folder | 2020-12-02 | 2020-12-02 | 1
5.3 | Phase 3 Source | 2020-12-03 | 2020-12-09 | 7 | Will follow the design phase
5.3.1 | Complete and submit Phase 3 Source code to Assignment folder | 2020-12-09 | 2020-12-09 | 1
6 | Testing | 2020-11-19 | TBD |  |  | Jonathan
6.1 | Perform testing |  |  |  | Will be performed following completion of the test plan
7 | User’s Guide | 2020-11-11 | 2020-12-08 | 28 |  | Cynthia
7.1 | Submit outline to GitHub | 2020-11-11 | 2020-11-13 | 3
7.2 | Submit preliminary user's guide | 2020-11-14 | 2020-11-17 | 4
7.3 | Complete and submit User’s Guide to GitHub | 2020-11-18 | 2020-12-08 | 21
8 | Submit final project deliverables to Assignment folder | 2020-12-15 | 2020-12-15 | 1 |  | Cynthia